# Rite Aid AI Risk Register — Version 1

Independent Historical AI Governance Case Study

Purpose: Identify, assess, and document AI-related risks associated with the historical facial recognition issues examined in the FTC's Rite Aid case.

Disclaimer: This is an independent educational simulation based on publicly available historical records. It is not affiliated with Rite Aid and does not represent Rite Aid's current AI governance program. Risk ratings, owners, and proposed controls are hypothetical recommendations unless explicitly supported by cited sources.

AI Risk Register

| Risk ID | Risk Description | Impact | Likelihood | Proposed Owner | Proposed Control | Status |
| --- | --- | --- | --- | --- | --- | --- |
| R-001 | Facial recognition could incorrectly identify a customer as someone previously suspected of theft | High — Possible customer harm, reputational damage, and legal consequences | Medium — Provisional simulation rating; historical frequency not independently established here | AI Governance Lead | Test false-match rates, document accuracy limitations, and require human verification before action | Proposed — Not implemented in simulation |
| R-002 | AI-driven identification errors or inappropriate staff responses could lead to unfair treatment of customers. | High — Potential discriminatory outcomes, customer harm, and legal exposure | Medium — Provisional simulation rating; not a measured historical probability | Compliance and Privacy Officer | Perform fairness testing, document escalation procedures, train staff, and prohibit action based solely on an AI match | Proposed — Not implemented in simulation |
| R-003 | Without sufficient monitoring, inaccurate results, complaints, or recurring incidents may remain unresolved. | High — Continued customer harm and weakened accountability | Medium — Provisional simulation rating; depends on assumed control weaknesses | AI Risk and Compliance Manager | Maintain incident logs, investigate complaints, review performance regularly, and establish stop-use triggers | Proposed — Not implemented in simulation |

Sources and Assessment Notes

1. Federal Trade Commission (FTC). (2023, December 19). Rite Aid Banned from Using AI Facial Recognition After FTC Says Retailer Deployed Technology without Reasonable Safeguards.

https://search.ftc.gov/news-events/news/press-releases/2023/12/rite-aid-banned-using-ai-facial-recognition-after-ftc-says-retailer-deployed-technology-without

2. Federal Trade Commission (FTC). FTC v. Rite Aid Corporation, Case No. 2:23-cv-5023. Includes the December 2023 complaint and March 2024 stipulated order.

https://www.ftc.gov/legal-library/browse/cases-proceedings/2023190-rite-aid-corporation-ftc-v

3. National Institute of Standards and Technology (NIST). (2023). Artificial Intelligence Risk Management Framework (AI RMF 1.0), NIST AI 100-1.

https://nvlpubs.nist.gov/nistpubs/ai/NIST.AI.100-1.pdf

Assessment Notes:

- Historical context: The FTC's complaint alleged failures relating to facial recognition accuracy, customer harm, and insufficient monitoring.

- Simulation assumptions: The impact and likelihood ratings are illustrative judgments made for this educational case study.

- Proposed controls and owners: These are recommendations, not verified existing Rite Aid practices.

- Framework alignment: Risk identification, assessment, prioritization, and response are informed by NIST AI RMF's GOVERN, MAP, MEASURE, and MANAGE functions.

- Regulatory distinction: FTC orders and NIST's voluntary guidance have different legal statuses; NIST AI RMF is not itself a binding regulation.

- Implementation status: All listed controls remain proposed within this simulation.